**Sri Lanka Blue Swimming Crab Fisheries**

**Improvement Project**

|  |  |
| --- | --- |
| **Month** | **Milestones 2013** |
|  |  |
| **May** | * **Sri Lankan Blue Swimming Crab Sustainable Fishery Stakeholder Workshop, Negombo 10th May 2013**
* **SLBSC FIP Pre Assessment Proposal & Budget Submitted to NFI CC Funding. Approved**
 |
|  |  |
| **August****September** | * **Fishery Assessment Field Survey and Report**
* **Scoping Document in three languages**
 |
|  |  |
| **October****November** | * **Consultations with Steering Committee Members (*i.e.,* producers, processors, regulators) and partners (*e.g.,* FAO UN, ILO UN, UNDP, IOM)**
* **Draft Development Work Plan; Implementation Plan; FIP Budget, Logic Model; Performance Monitoring and Impact Evaluation Framework**
* **Launch of the SLBSC FIP, SLBSC web page and SEASL website by the Minister of Fisheries and Aquatic Resources on 31st October 2013**
* **Financial Settlement and Report**
 |
|  |  |
| **December** | * **Interim SLBSC FIP funding requests to NFI CC for 2013 – 2014 submitted. Not approved.**
 |